Topic: Project Design and Outline

Tripti Vishwakarma

Colorado State University Global

Course Code: CSC 501-2

Bingdong Li

Aug 11 2024

Project Plan for the Design and Outline of a Software Life Expectancy Model

1. Project Overview

- Project Name: Design and Implementation of a Software Life Expectancy Model

- Project Manager: Tripti Vishwakarma

- Start Date: September 15, 2024

- End Date: January 19, 2025

- Project Sponsor: XYZ Software Solutions

- Budget: $150,000

2. Project Objectives

- Develop a predictive model to estimate the software’s life expectancy.

- Integrate the model with the existing software program.

- Validate the model's accuracy through testing and real-world data.

- Provide comprehensive documentation and training for stakeholders.

3. Scope

- Project Scope:

  - Model Development: Create a predictive model using historical and real-time data.

  - Integration: Embed the model into the current software ecosystem.

  - Testing and Validation: Conduct rigorous testing and validation to ensure accuracy.

  - Documentation and Training: Prepare detailed documentation and provide training sessions for stakeholders.

4. Budget

- Total Budget: $150,000

| Category | Estimated Cost |
| --- | --- |
| Personnel | $80,000 |
| Software and Tools | $20,000 |
| Training and Documentation | $15,000 |
| Contingency | $10,000 |
| Miscellaneous | $25,000 |
| Total | $150,000 |

5. Resources

- Personnel:

  - Project Manager: Tripti Vishwakarma

  - Business Analyst: Jane Dwen

  - Data Scientist: John Smith

  - Software Developer: Alice Johnson

  - QA Tester: Bob Brown

  - Technical Writer: Carol White

  - Trainer: Dave Green

- Tools and Technologies:

  - Project Management Software: Jira, Trello

  - Data Analysis Tools: Python, R

  - Development Environment: Visual Studio, Eclipse

  - Version Control System: Git

  - Testing Tools: Selenium, JUnit

  - Documentation Tools: Confluence, MS Word

6. Stakeholder Analysis

- Primary Stakeholders:

  - XYZ Software Solutions: Project sponsor providing overall direction and funding.

  - End Users: Users of the software who will benefit from the life expectancy model.

  - Development Team: Responsible for implementing and integrating the model.

- Secondary Stakeholders:

  - Regulatory Bodies: Ensure compliance with data protection laws.

  - Training Participants: Receive training on the new model and documentation.

7. Project Timeline

| Phase | Start Date | End Date | Duration |
| --- | --- | --- | --- |
| Project Initiation | Sep 15, 2024 | Sep 21, 2024 | 1 week |
| Requirements Gathering | Sep 22, 2024 | Oct 5, 2024 | 2 weeks |
| Design | Oct 6, 2024 | Oct 19, 2024 | 2 weeks |
| Development | Oct 20, 2024 | Dec 1, 2024 | 6 weeks |
| Integration | Dec 2, 2024 | Dec 15, 2024 | 2 weeks |
| Testing & Validation | Dec 16, 2024 | Dec 29, 2024 | 2 weeks |
| Documentation & Training | Dec 30, 2024 | Jan 12, 2025 | 2 weeks |
| Project Closure | Jan 13, 2025 | Jan 19, 2025 | 1 week |

8. Possible Change Requests and Goal Alignments

- Change Requests:

  - Scope Changes: Adjustments in model complexity or additional features.

  - Budget Adjustments: Reallocation due to unforeseen expenses or additional requirements.

  - Timeline Modifications: Shifts in deadlines due to development or integration challenges.

- Goal Alignments:

  - Review Meetings: Regular meetings with stakeholders to ensure alignment with objectives and manage expectations.

  - Scope Management: Formal change control procedures to address scope changes and align with overall project goals.

9. Project Management Approach

- Methodologies:

  - Agile Methodology: For iterative development and flexibility.

  - Waterfall Methodology: For phases with well-defined requirements.

- Communication Plan:

  - Weekly Status Meetings: With the project team.

  - Bi-weekly Progress Reports: To stakeholders.

  - Monthly Review Meetings: With senior management.

  - Ad-hoc Meetings: For urgent issue resolution.

- Risk Management:

  - Risk Identification: Issues related to requirements, integration, technical challenges, and data availability.

  - Risk Mitigation: Thorough requirements analysis, iterative testing, buffer time allocation, and data validation strategies.

10. Project Closure

- Activities:

  - Finalize Deliverables: Ensure all deliverables meet stakeholder expectations and obtain formal approval.

  - Post-Project Review: Conduct a review to capture lessons learned and areas for improvement.

  - Documentation: Archive all project documentation and materials.

  - Resource Release: Release project resources and formally close the project.

Diagrams and Charts

- Work Breakdown Structure (WBS): Visual representation of project deliverables and tasks.

- Gantt Chart: Timeline visualization of project phases and milestones.

### Project Outline

Project Name: Design and Implementation of a Software Life Expectancy Model

Project Manager: Tripti Vishwakarma

Start Date: September 15, 2024

End Date: January 19, 2025

Budget: $150,000

### 1. Project Scope

Objectives:

- Develop a predictive model to estimate software life expectancy.

- Integrate the model with the existing software systems.

- Validate the model’s accuracy with real-world data.

- Provide comprehensive documentation and training for stakeholders.

Deliverables:

- Predictive Model: Functional model for estimating software life expectancy.

- Integration: Model integrated with existing software systems.

- Validation Report: Documentation of testing and validation results.

- Documentation: Manuals, technical documentation, training materials.

- Training: Training sessions and workshops for stakeholders.

Out of Scope:

- Major software updates beyond integration.

- Long-term support beyond initial training and documentation.

### 2. Project Timeline

Phase 1: Project Initiation

- Start Date: September 15, 2024

- End Date: September 21, 2024

- Duration: 1 week

- Activities: Kickoff meeting, stakeholder alignment, initial planning.

Phase 2: Requirements Gathering

- Start Date: September 22, 2024

- End Date: October 5, 2024

- Duration: 2 weeks

- Activities: Collect and document requirements, stakeholder interviews.

Phase 3: Design

- Start Date: October 6, 2024

- End Date: October 19, 2024

- Duration: 2 weeks

- Activities: Design model architecture, create design specifications.

Phase 4: Development

- Start Date: October 20, 2024

- End Date: December 1, 2024

- Duration: 6 weeks

- Activities: Develop predictive model, initial integration with systems.

Phase 5: Integration

- Start Date: December 2, 2024

- End Date: December 15, 2024

- Duration: 2 weeks

- Activities: Complete model integration, resolve issues.

Phase 6: Testing & Validation

- Start Date: December 16, 2024

- End Date: December 29, 2024

- Duration: 2 weeks

- Activities: Conduct tests, validate accuracy, prepare report.

Phase 7: Documentation & Training

- Start Date: December 30, 2024

- End Date: January 12, 2025

- Duration: 2 weeks

- Activities: Prepare documentation, conduct training sessions.

Phase 8: Project Closure

- Start Date: January 13, 2025

- End Date: January 19, 2025

- Duration: 1 week

- Activities: Finalize deliverables, obtain approval, conduct review.

Maintenance Phase:

- Start Date: January 20, 2025

- End Date: TBD

- Activities: Monitor performance, provide support, address issues.

### Notes:

- Change Requests: Any changes in scope or timelines will follow a formal change management process.

- Goal Alignment: Regular reviews will ensure alignment with project objectives and stakeholder expectations.

References

- Project Management Institute. (2021). A Guide to the Project Management Body of Knowledge (PMBOK Guide). Project Management Institute.

- Kerzner, H. (2019). Project Management: A Systems Approach to Planning, Scheduling, and Controlling. Wiley.

- Fisher, R., & Ury, W. (1981). Getting to Yes: Negotiating Agreement Without Giving In. Penguin Books.